## Slide 1: October 28….HR, Communications and Procurement
Human Resources--Resource Leveling
Communications Knowledge Management
Procurement Knowledge Management

## Slide 2: Resource Loading and Leveling
Resource loading refers to the amount of individual resources an existing project schedule requires during specific time periods
Resource histograms show resource loading
Over-allocation means more resources than are available are assigned to perform work at a given time

## Slide 3: Figure 9-7. Sample Histogram Showing an Over-allocated Individual
Project 98 file

## Slide 4: Resource Leveling
Resource leveling is a technique for resolving resource conflicts by delaying tasks
The main purpose of resource leveling is to create a smoother distribution of resource usage and reduce over-allocation
Resource Leveling is used all of the time when the scheduling is resource-constrained

## Slide 5: Figure 9-8. Resource Leveling Example

## Slide 6: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
Focus on rewarding teams for achieving specific goals
Allow time for team members to mentor and help each other to meet project goals and develop human resources

## Slide 7: General Advice on Teams
Focus on meeting project objectives and producing positive results
Fix the problem instead of blaming people
Establish regular, effective meetings
Nurture team members and encourage them to help each other
Acknowledge individual and group accomplishments

## Slide 8: Using Software to Assist in Human Resource Management
Software can help in producing RAMS and resource histograms
Project management software includes several features related to human resource management such as
  viewing resource usage information
  identifying under and over-allocated resources
  leveling resources

## Slide 9: The Bottom Line for HR Management
Respect, reward your team
  Treat them with dignity and professionalism
Build rapport with your team
Motivate them using their ‘hot buttons’
Articulate the goal, articulate the reality and use the resulting tension to pull performance toward the goal

## Slide 10: Chapter 10: Project Communications Management
Notes: PM’s spend 90% of their time communicating

## Slide 11: Importance of Good Communications
The greatest threat to many projects is a failure to communicate
Our culture does not portray IT professionals as being good communicators
Research shows that IT professionals must be able to communicate effectively to succeed in their positions
Strong verbal skills are a key factor in career advancement for IT professionals
Notes: Project Managers spend 90% of their time communicating

## Slide 12: Project Communications Management Processes
Plan Communications: determining the information and communications needs of the stakeholders
Manage Communications: making needed information available in a timely manner and collecting and disseminating performance information
Control Communications: generating, gathering, and disseminating information to formalize phase or project completion

## Slide 13: Project Communications Management Processes—5th edition
Plan Communications
Manage Communications
Control Communications
What process groups do these processes belong?
  The process groups are Initiating, Planning, Execution, Closing, and monitoring/controlling

## Slide 14: Communications Planning
Every project should include some type of communications management plan, a document that guides project communications
Creating a stakeholder analysis for project communications also aids in communications planning
It is better to over communicate than to under communicate

## Slide 15: Communications Management Plan Contents
A description of a collection and filing structure for gathering and storing various types of information
A distribution structure describing what information goes to whom, when, and how
A format for communicating key project information

## Slide 16: Communications Management Plan Contents, continued
A project schedule for producing the information
Access methods for obtaining the information
A method for updating the communications management plans as the project progresses and develops
A stakeholder communications analysis

## Slide 17: Table 10-1. Sample Stake holder Analysis for Project Communications

## Slide 18: Information Distribution
Getting the right information to the right people at the right time and in a useful format is just as important as developing the information in the first place
Important considerations include
  using technology to enhance information distribution
  formal and informal methods for distributing information

## Slide 19: What Went Wrong?
A well publicized example of misuse of e-mail comes from the 1998 Justice Department's high profile, antitrust suit against Microsoft. E-mail emerged as a star witness in the case. Many executives sent messages that should never have been put in writing. The court used e-mail as evidence, even though the senders of the notes said the information was being interpreted out of context.
Some companies, such as Amazon.com, have established policies to encourage employees to watch their use of e-mail and delete it often. Their "Sweep and Clean" program instructed employees to purge e-mails that were no longer required for business or legal purposes. They even offered free café lattes to employees who complied immediately.
Harmon, Amy, "E-mail comes back to haunt companies," November 29, 1998

## Slide 20: Figure 10-1. The Impact of the Number of People on Communications Channels

## Slide 21: Performance Reporting
Performance reporting keeps stakeholders informed about how resources are being used to achieve project objectives
  Status reports describe where the project stands at a specific point in time
  Progress reports describe what the project team has accomplished during a certain period of time
  Project forecasting predicts future project status and progress based on past information and trends
  Status review meetings often include performance reporting

## Slide 22: Administrative Closure
A project or phase of a project requires closure
Administrative closure produces
  project archives
  formal acceptance
  lessons learned

## Slide 23: Suggestions for Improving Project Communications
Resolve conflicts effectively
Develop better communication skills
Run effective meetings
Use templates for project communications

## Slide 24: Conflict Handling Modes, in Preference Order
Confrontation or problem-solving: directly face a conflict
Compromise: use a give-and-take approach
Smoothing: de-emphasize areas of differences and emphasize areas of agreement
Forcing: the win-lose approach
Withdrawal: retreat or withdraw from an actual or potential disagreement

## Slide 25: Table 10-3. Sample Template for a Monthly Progress Report

## Slide 26: Table 10-5. Sample Template for a Letter of Agreement for a Class Project

## Slide 27: Figure 10-3. Gantt Chart Template for a Class Project
Project 98 file

## Slide 28: Table 10-6. Guidance for Student’s Lessons Learned Report
Every two weeks or after a major event in your group project, write a brief journal entry describing what happened and how you felt about it. At the end of the term, write a 2-3 page paper describing your lessons learned based on your group project. Answer the following questions:
  What were your roles and responsibilities on the team? How were they decided?
  What did you like/dislike about the project?
  What did you learn about project management and yourself by doing the project?
  What did you learn about teamwork and yourself by doing the project?
  What would you have done differently? What will you remember to do on the next project you work on after this experience?

## Slide 29: Developing a Communications Infrastructure
A communications infrastructure is a set of tools, techniques, and principles that provide a foundation for the effective transfer of information
  Tools include e-mail, project management software, groupware, fax machines, telephones, teleconferencing systems, document management systems, and word processors
  Techniques include reporting guidelines and templates, meeting ground rules and procedures, decision-making processes, problem-solving approaches, and conflict resolution and negotiation techniques
  Principles include using open dialog and an agreed upon work ethic

## Slide 30: Using Software to Assist in Project Communications
There are many software tools to aid in project communications
The “What Went Right?” example on pg. 264 describes several new web-based and wireless communications tools
Microsoft Project includes several features to enhance communications

## Slide 31: Figure 10-4. MS Project Information Saved as HTML File
Project 98 file

## Slide 32: Procurement
A widely tested knowledge areas on the CAPM and PMP EXAMS
By the way I am batting 100% for my students who have successfully taken the CAPM or PMP exams in the last month—one of each.

## Slide 33: Learning Objectives--Proccurement
Understand the importance of project procurement management and the increasing use of outsourcing for information technology (IT) projects
Describe the work involved in planning procurements for projects, including determining the proper type of contract to use and preparing a procurement management plan, statement of work, source selection criteria, and make-or-buy analysis
Discuss how to conduct procurements and strategies for obtaining seller responses, selecting sellers, and awarding contracts

## Slide 34: Learning Objectives (cont’d)
Understand the process of controlling procurements by managing procurement relationships and monitoring contract performance
Describe the process of closing procurements
Discuss types of software that are available to assist in project procurement management

## Slide 35: Importance of Project Procurement Management
Procurement means acquiring goods and/or services from an outside source
Other terms include purchasing and outsourcing
Experts predict that global spending on computer software and services will continue to grow
People continue to debate whether offshore outsourcing helps their own country or not

## Slide 36: Debates on Outsourcing
Some companies, such as Wal-Mart, prefer to do no outsourcing at all, while others do a lot of outsourcing. GM recently announced plans to switch from outsourcing 90% of IT service to only 10%
Most organizations do some form of outsourcing to meet their IT needs and spend most money within their own country
The U.S. temporary workforce continues to grow as people work for temporary job agencies so they can more easily move from company to company
Notes: Outsourcing the IT function has its disadvantages…one of those is that the outsourcer has to make all changes to supporting software for all business processes.

## Slide 37: IT Outsourcing Market Continues to Grow
U.S. companies are transferring more work abroad, especially in the areas of IT infrastructure, application development and maintenance, and innovation processes
India, China, and the Philippines are the preferred locations for outsourcing, and Latin America is growing in popularity
A shortage of qualified personnel, not cost savings, is the top reason for global outsourcing of IT services

## Slide 38: Why Outsource?
To access skills and technologies
To reduce both fixed and recurrent costs
To allow the client organization to focus on its core business
To provide flexibility
To increase accountability

## Slide 39: Contracts
A contract is a mutually binding agreement that obligates the seller to provide the specified products or services and obligates the buyer to pay for them
Contracts can clarify responsibilities and sharpen focus on key deliverables of a project
Because contracts are legally binding, there is more accountability for delivering the work as stated in the contract
A recent trend in outsourcing is the increasing size of contracts

## Slide 40: What Went Wrong?
In 2011, New York City’s mayor, Michael Bloomberg, acknowledged that City Hall had mismanaged its major IT projects and vowed to improve their oversight
For example, prosecutors said the $700 million price tag for the CityTime payroll system was inflated by fraud, and the mayor demanded $600 million back from the main contractor
The automated personnel system, Nycaps, suffered significant delays and cost overruns due to leadership issues, increasing from an original estimate of $66 million to over $363 million

## Slide 41: Project Procurement Management Processes—5th Edition of PMBOK
Project procurement management: Acquiring goods and services for a project from outside the performing organization
Processes include:
  Plan procurement management: Determining what to procure and when and how to do it
  Conduct procurements: Obtaining seller responses, selecting sellers, and awarding contracts
  Control procurements: Managing relationships with sellers, monitoring contract performance, and making changes as needed
  Close procurements: Completing and settling each contract or agreement, including resolving of any open items

## Slide 42: Figure 12-1. Project Procurement Management Summary

## Slide 43: Planning Procurement Management
Identifying which project needs can best be met by using products or services outside the organization
If there is no need to buy any products or services from outside the organization, then there is no need to perform any of the other procurement management processes

## Slide 44: What Went Right?
Several organizations, such as The Boots Company PLC in England, outsource their IT services to save money compared with the cost of running the systems themselves
Carefully planning procurement can also save millions of dollars, as the U.S. Air Force did by using a unit pricing strategy for a large office automation project

## Slide 45: Types of Contracts
Different types of contracts can be used in different situations:
  Fixed price or lump sum contracts: Involve a fixed total price for a well-defined product or service
  Cost reimbursable contracts: Involve payment to the seller for direct and indirect costs
  Time and material contracts: Hybrid of both fixed price and cost reimbursable contracts, often used by consultants
  Unit price contracts: Require the buyer to pay the seller a predetermined amount per unit of service
A single contract can actually include all four of these categories, if it makes sense for that particular procurement

## Slide 46: Point of Total Assumption
The Point of Total Assumption (PTA) is the cost at which the contractor assumes total responsibility for each additional dollar of contract cost
Contractors do not want to reach the point of total assumption, because it hurts them financially, so they have an incentive to prevent cost overruns
The PTA is calculated with the following formula:
PTA = (ceiling price – target price)/government share + target cost

## Slide 47: Cost Reimbursable Contracts
Cost plus incentive fee (CPIF): The buyer pays the supplier for allowable performance costs plus a predetermined fee and an incentive bonus
Cost plus fixed fee (CPFF): The buyer pays the supplier for allowable performance costs plus a fixed fee payment usually based on a percentage of estimated costs
Cost plus percentage of costs (CPPC): The buyer pays the supplier for allowable performance costs plus a predetermined percentage based on total costs

## Slide 48: Figure 12-2. Contract Types Versus Risk

## Slide 49: Media Snapshot
Contract incentives can be extremely effective. On August 1, 2007, tragedy struck Minneapolis, Minnesota, when a bridge on I-35W collapsed, killing 13 motorists, injuring 150 people, and leaving a mass of concrete and steel in the river and on its banks
Peter Sanderson, project manager for the joint venture of Flatiron-Manson led his team in completing the project. The contractors earned $25 million in incentive fees on top of their $234 million contract for completing the bridge three months ahead of schedule
MnDOT justified the incentive payment by saying that each day the bridge was closed it cost road users more than $400,000

## Slide 50: Contract Clauses
Contracts should include specific clauses to take into account issues unique to the project
Can require various educational or work experience for different pay rights
A termination clause is a contract clause that allows the buyer or supplier to end the contract

## Slide 51: Tools and Techniques for Planning Purchases and Acquisitions
Expert judgment
Market research
Make-or-buy analysis: General management technique used to determine whether an organization should make or perform a particular product or service inside the organization or buy from someone else

## Slide 52: Make-or-Buy Example
Assume you can lease an item you need for a project for $800/day. To purchase the item, the cost is $12,000 plus a daily operational cost of $400/day
How long will it take for the purchase cost to be the same as the lease cost?

## Slide 53: Make-or Buy Solution
Set up an equation so both options, purchase and lease, are equal
In this example, use the following equation. Let d be the number of days to use the item:
  $12,000 + $400d = $800d
  Subtracting $400d from both sides, you get:
  $12,000 = $400d
  Dividing both sides by $400, you get:
  d = 30
If you need the item for more than 30 days, it is more economical to purchase it

## Slide 54: Procurement Management Plan
Describes how the procurement processes will be managed, from developing documentation for making outside purchases or acquisitions to contract closure
Contents varies based on project needs

## Slide 55: Contract Statement of Work (SOW)
A statement of work is a description of the work required for the procurement
If a SOW is used as part of a contract to describe only the work required for that particular contract, it is called a contract statement of work
A SOW is a type of scope statement
A good SOW gives bidders a better understanding of the buyer’s expectations

## Slide 56: Figure 12-3. Statement of Work (SOW) Template

## Slide 57: Procurement Documents
Request for Proposals: Used to solicit proposals from prospective sellers
  A proposal is a document prepared by a seller when there are different approaches for meeting buyer needs
Requests for Quotes: Used to solicit quotes or bids from prospective suppliers
  A bid, also called a tender or quote (short for quotation), is a document prepared by sellers providing pricing for standard items that have been clearly defined by the buyer

## Slide 58: Figure 12-4. Request for Proposal (RFP) Template

## Slide 59: Source Selection Criteria
It’s important to prepare some form of evaluation criteria, preferably before issuing a formal RFP or RFQ
Beware of proposals that look good on paper; be sure to evaluate factors, such as past performance and management approach
Can require a technical presentation as part of a proposal

## Slide 60: Conducting Procurements
Deciding whom to ask to do the work
Sending appropriate documentation to potential
sellers
Obtaining proposals or bids
Selecting a seller
Awarding a contract

## Slide 61: Approaches for Procurement
Organizations can advertise to procure goods and services in several ways:
  Approaching the preferred vendor
  Approaching several potential vendors
  Advertising to anyone interested
A bidders’ conference can help clarify the buyer’s expectations

## Slide 62: Figure 12-5. Sample Proposal Evaluation Sheet

## Slide 63: Seller Selection
Organizations often do an initial evaluation of all proposals and bids and then develop a short list of potential sellers for further evaluation
Sellers on the short list often prepare a best and final offer (BAFO)
Final output is a contract signed by the buyer and the selected seller

## Slide 64: Controlling Procurements
Ensures that the seller’s performance meets contractual requirements
Contracts are legal relationships, so it is important that legal and contracting professionals be involved in writing and administering contracts
It is critical that project managers and team members watch for constructive change orders, which are oral or written acts or omissions by someone with actual or apparent authority that can be construed to have the same effect as a written change order

## Slide 65: Global Issues
A recent trend is to hire people in rural areas of the same country to perform work, often at less cost. Rural sourcing uses two simple premises: Smaller towns need jobs, and workers there often charge 25 to 50 percent less than their urban counterparts.
  Onshore Technology Services recruits workers from low-paying jobs and gives them intensive training in IT specialties. The company employs 65 people in IT centers in the rural Missouri towns of Macon, Lebanon, and Joplin
  CrossUSA recruits older IT workers who are nearing retirement and want to enjoy a small-town quality of life. The company has 100 employees in Sebeka, Minnesota (population 700) and Eveleth, Minnesota (population 3,000)

## Slide 66: Suggestions for Change Control in Contracts
Changes to any part of the project need to be reviewed, approved, and documented by the same people in the same way that the original part of the plan was approved
Evaluation of any change should include an impact analysis. How will the change affect the scope, time, cost, and quality of the goods or services being provided?
Changes must be documented in writing. Project team members should also document all important meetings and telephone calls

## Slide 67: Suggestions for Change Control in Contracts (cont’d)
Project managers and teams should stay closely involved to make sure the new system will meet business needs and work in an operational environment
Have backup plans
Use tools and techniques, such as a contract change control system, buyer-conducted performance reviews, inspections and audits, and so on

## Slide 68: Best Practice
Accenture developed a list of best practices from experienced outsourcers throughout the world:
  Build in Broad Business Outcomes Early and Often
  Hire a Partner, Not Just a Provider
  It’s More Than a Contract, It’s a Business Relationship
  Leverage Gain-Sharing
  Use Active Governance
  Assign a Dedicated Executive
  Focus Relentlessly on Primary Objectives

## Slide 69: Closing Procurements
Involves completing and settling contracts and resolving any open items
The project team should:
    Determine if all work was completed correctly and satisfactorily
    Update records to reflect final results
    Archive information for future use
The contract itself should include requirements for formal acceptance and closure

## Slide 70: Tools to Assist in Contract Closure
Procurement audits identify lessons learned in the procurement process
Negotiated settlements help close contracts more smoothly
A records management system provides the ability to easily organize, find, and archive procurement-related documents

## Slide 71: Using Software to Assist in Project Procurement Management
Word processing software helps write proposals and contracts, spreadsheets help evaluate suppliers, databases help track suppliers, and presentation software helps present procurement-related information
E-procurement software does many procurement functions electronically
Organizations also use other Internet tools to find information on suppliers or auction goods and services

## Slide 72: Chapter Summary
Project procurement management involves acquiring goods and services for a project from outside the performing organization
Processes include:
  Plan procurement management
  Conduct procurements
  Control procurements
  Close procurements