ISQS 4350 Operations Management

Practice Final  with answers at the end

This exam consists of multiple choice and discussion problems.   The discussion problems are worth 50% of the exam grade.  The multiple-choice part is worth 50% of the exam grade.  For the multiple-choice part, record your answers on the orange answer sheet provided.  Each multiple choice question is worth one point.

- In MS Project, which button do you click for subordination?

  - Link

  - Indent

  - Resource assign

  - Resource sheet

- In MS Project, which button do you click on to indicate precedence?

  - Link

  - Indent

  - Resource assign

  - Resource sheet

- In MS Project to view project cost and duration, you must click on

  - Project on the menu bar, then project information and then statistics

  - Tools on the menu bar and then Project information underneath

  - Functions on the menu bar and then project statistics underneath

- In MS Project, to see the activity and phase costs you must

  - Change the table in the Gantt view to “cost”

  - Insert a cost column in the entry table next to the duration column

  - Print a cost report

  - Any of the above

- For MS Project to cost your project, it needs to know

- resource hourly costs

- activity fixed costs

- stakeholder charges

- all of the above

- a and b only

6.  In MS Project, durations of phases containing one or more subordinate tasks, can be

  - changed manually by the user

  - specified only by MS Project

  - none of the above

  - a or b only

7.  In MS Project, task information is entered in which view?

a.  Resource sheet

b.  PERT chart

c.  Gantt chart

d.  task sheet

8.  .  In MS Project, the view that exhibits the network diagram is the _______.

a.  Resource sheet

b.  PERT chart

c.  Gantt chart

d.  task sheet

9.  In MS Project, the critical path is _____.

a.  exhibited in red

b.  not calculated or found

c.  exhibited on the PERT chart only

d.  replaced with the critical chain

10.  MS Project makes the following assumptions regarding time.

a.  8-hour work days

b.  no work on Sat. or Sun.

c.  flex work schedule

d.  all of the above

e.  a and b only

11.   To use MS Project to track a planned project, one must first ____.

a.  view the network diagram

b.  save the project plan as a baseline

c.  create a project track

d.  calculate the earned value

12.  There are four stages in the project management lifecycle.  Which is not one of the stages?

a.  Definition and Conceptualization

b.  Management and Measurement

c.  Planning and Budgeting

d.  Execution and Control

e.  Termination and closure

### 13.  In which of the stages is scope management mostly involved?

a.  Definition and Conceptualization

b.  Management and Measurement

c.  Planning and Budgeting

d.  Execution and Control

e.  Termination and closure

14.  In which of the stages is time management mostly involved?

a.  Definition and Conceptualization

b.  Management and Measurement

c.  Planning and Budgeting

d.  Execution and Control

e.  Termination and closure

15. The main purpose of a project plan is to

### a. acquire resources

### b.  guide project execution.

### c.  meet standards expectations.

### d.  reduce risk.

## 16. The WBS is an output of what knowledge area?

### a.  Integration

### b.  Scope

### c.  Cost

### d.  Quality

17.  According to PMBOK, activity definition is a _____.

a.  subproject

b.  process

c.  plan

d.  problem

## 18. Activity definition is a part of what knowledge area?

### a.  Integration

### b.  Time

### c.  Cost

### d.  Quality

## 19. During project execution

### a.  Project goals and scope are highlighted.

### b.  the products of the project are produced.

### c.  overall key stakeholder analysis is provided.

### d.  the WBS is scheduled.

## 20.  Project execution involves taking actions to

### a.  establish a good plan.

### b.  close out the project.

### c.  ensure that activities in the project plan are completed.

### d.  provide feedback to key vendors.

## 21.  The most important output of project execution is

### a.  change requests.

### b.  work products.

### c.  stakeholder analysis.

### d.  the WBS.

Questions 22 through 31 relate to Goldratt’s book Critical Chain.

22. In the book Critical Chain Goldratt suggests that project team members and managers put too much _____ into the estimated durations of the tasks they are asked to complete.

- effort

- planning

- control

- safety

- resources

23.  In the classroom discussions of failed projects, there was a tendency _____.

- to place blame outside the organization

- to place blame on the organization itself

- neither of these

24.  What is the name of the principal role player?

- Alex Rojo

- Richard Silver

- Bill Crutchfield

- Jonah

- Johnny Fisher

25.  Measurements should _____.

- always be accurate to six sigma levels

- measure cost, productivity and schedule variances

- induce the parts to do what is good for the system as a whole

- all of the above

- a and b only

26.  Which one of the following is not one of the five steps that make up the Theory of Constraints?

- IDENTIFY the project constraint

- Decide how to EXTRAPOLATE that constraint

- SUBORDINATE everything to that decision

- ELEVATE the system’s constraint

- Go back to step a

27. Goldratt believes that conflicts are usually based on _____.

- unclear assignment of responsibilities and roles

- faulty assumptions

- personality clashes

- all of the above

- a and c only

28.  To resolve conflicts, Goldratt uses a device called _______.

- a current reality tree

- an evaporating cloud

- a future reality tree

- a prerequisite tree

- a transition tree

29.  For the project manager to retain focus, Goldratt recommends

- placing a time buffer at the point where non-critical paths intersect with the critical path

- having the project leader do all of the team-related technology management

- that the project manager not work on more than two projects at the same time

- all of the above

- a and c only

30.  Such measures as BCWP, BCWS, ACWP Goldratt is ______.

- in favor of

- strongly in favor of

- neutral toward

- strongly opposed to

31. Procrastination is referred to as the _____.

- worst enemy of all projects

- student syndrome

- earliest start strategy

- all of the above

32. If you have a task on the critical path and your time to complete your task has arrived, then Goldratt recommends _____.

- that you drop everything else and work just on your task until it is complete

- that you make completion of the task a high priority

- that you acquire additional resources

- that you assess whether you can actually do the task by its due date first before doing anything else

33.  An activity has probabilistic completion times of 20, 30 and 46.  What is its mean time?

- 16

- 43

- 21

- 31

e.    None of these

34.  For the activity described above with probabilistic completion times of 20, 30 and 46, what is the variance of the completion time?

- 15.44

- 18.78

- 26.52

- 34.33

- none of these

35.  Any technique that uses only one time estimate is considered to be a ______________ technique.

a.  Deterministic

b.  Stochastic

c.  Probabilistic

d.  Random

36.  Determining the earned value involves collecting data on the percent complete for each work package and then converting this percentage to a dollar amount by multiplying the _________________ of the work package by the percent complete.

a.  budgeted cost

b.  duration

c.  total cumulative fees

d.  contract cumulating amount

37.  The cumulative earned value for each work package is calculated by multiplying each percent complete by the ________________ for the work package.

a.  total budgeted cost

b.  cumulative budgeted cost

c.  total cumulative fees

d.  contract cumulating amount

38.  _________________ is the difference between the cumulative earned value of the work performed and the cumulative actual cost.  It is also the difference between BCWP (=earned value) and ACWP (Actual cost of Work Performed).

a.  Cost performance index

b.  Cost variance

c.  Budgeted costs

d.  Cost quality index

39.   A work package is 70% done and $200,000 was budgeted for it.  What is its BCWP?

- $140,000

- $80,000

- simply the value earned

- all of the above

- a and c only

40.  BCWS stands for ______.

- Budgeted Cost of Work Studied

- Budget Cumulative of Working Students

- Budgeted Cost of Work Scheduled

- None of the above

41.  If the work package in 39 above has an ACWP of $100,000 then ______.

- cost variance is $20,000

- cost variance is -$20,000

- the work package is over budget

- none of the above

- b and c only

42.  At this point in time the work package in 39 above should be 80% complete.  Then ____.

- schedule variance is $10,000

- the work package is behind schedule

- the work package is ahead of schedule

- a and c above

- none of the above

43.  Which of the following is not one of the stages of the CMM (capability maturity model)?

- INITIAL		b.  DEFINED

c.    REPEATABLE

d.   MEASURED

e.   OPTIMIZING

44.  How long does it take to go from one stage of the CMM to the next?

- one year at least

- six months at least

- two  years at least

- one quarter year at least

none of these

45.  Which of the following is a reason for the increased popularity of project management?

a) diversity of new products and product markets

b) shorter life span of products

c) rapid technological changes

d) all of the above

46.  Typically, project teams include individuals

a) from other areas in the organization

b) selected because of their special skills

c) from the functional area of the project

d) all of the above

47.  Which of the following is the primary focus of control in project management?

a) making sure all activities have been identified

b) identifying resource needs

c) establishing precedence relationships

d) maintaining the project schedule and making sure work is completed on time

48.  Which of the following defines the purpose of the WBS?

a) to identify activities

b) to determine project workloads

c) to identify subordination relationships between modules and activities

d) all of the above

49.  Which of the following statements concerning a Gantt chart is true?

a) Gantt charts are particularly helpful for scheduling and planning large projects.

b) Gantt charts are particularly helpful for scheduling and planning projects with complex precedence relationships.

c) The Gantt chart indicates where extra time is available and activities can be delayed.

d) The Gantt chart has been a popular project scheduling tool, but is not widely used now.

50.  All of the following are traditional project management techniques for scheduling and planning except

a) CPM

b) PLAN

c) Gantt Chart

d) PERT

51.  In a CPM/PERT network, an event refers to

a) the occurrence of a delay in the project

b) an activity inserted into the network to show a precedence relationship with no passage of time

c) the beginning or completion of an activity or project

d) the earliest an activity can start

52.  The critical path is referred to as the

a)  most direct path from the beginning node to the ending node

b) shortest path in terms of time

c) longest path in terms of time

d) path with the largest amount of slack time

53.  Activities on the critical path are critical because they

a) represent the maximum project completion time

b) cannot tolerate any delay in completion

c) represent the most expense in terms of resources

d) represent the largest and most complex activities of the project

Table 1

Time Estimates

Activity a    m     b   predecessors

-----------------------------------

A         6    10    14   --

B         8    9      13    A

C         4    12    20    A

D         6     8     10      B, C

-----------------------------------

54.  Using the data in Table 1 to calculate the expected time and variance for each activity, which of the following statements is true?

a) The expected time for activity C is 10.00.

b) The variance for activity B is 1.36.

c) The largest expected time occurs for activity B.

d) The largest variance is for activity C.

55.  Using the data in Table 1, what is the total project duration?

a) 30

b) 22

c) 25

d) 35

56.  Using the data in Table 1, what is the total project variance?

a) 2.78

b) 9.33

c) 23.00

d) none of the above

57.  What is the critical path?

a)  A-C-D

b)  A-C

c)  A-B-D

d)  A-B

e)  none of these

58.  What is the latest start time for C?

a)  15

b)  13

c)  19

d)  22

e)  none of these

# DISCUSSION PROBLEMS (50 points)

1. CRITICAL PATH (10 points)

MINIMUM 	PRECEDENT		CRASH

ACT.  DURATION     DUR            	ACTIVITY		COST/DAY

A	  3		2			-		$400

B	  3		3			A		$200

C	  5		2			A		$200

D	  4		4			B		$300

E	  7		5			B, C		$100

F	11		3			C		$400

G	  9		7			D,E,F		$100

Create the critical path for the list of tasks above.  Use an activity on node representation.  For each node, determine, the ES, EF, LS, LF and place these at their respective corners of each node.

2.  PERT CRASHING (10 points total)

Crash the PERT chart above assuming you have $1500 to spend and that activities cannot be shorter than their minimum durations.  Note that activity A can only be crashed 1 day, while activity B can not be crashed at all.  Try to achieve the greatest reduction in project duration for the least amount spent.

3.  Earned Value Analysis (15 points total)

In the above, assume tasks A, B & C all  started on 11/20/00.  Planned durations are in days and are the numbers in the boxes shown above.  A is 60% complete, B is 70% complete and C is 50% complete.  So far, $1800 has been spent on A, $2000 on B and $4000 on C.  The daily costs for A, B and C are $400, $500, $800, respectively.  The budget for A is 5*$400 or $2000.   Use today’s date to determine BCWS.   Assume 5-day work weeks, with no work being done on Saturday or Sunday.  For example, the BCWS for A is $2000.  Determine for A, B and C, BCWP, BCWS, ACWP, CV(=BCWP – ACWP), SV(=BCWP – BCWS).  Complete the following table.

(10 points)

| TASK | BUDGET | %COMP | ACWP | BCWS | BCWP | CV | SV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |
| TOTALS |  |  |  |  |  |  |  |

(5 points) Is the project behind schedule?  Over or under budget?  Will the entire project be delayed?

Formulas:

CV = BCWP – ACWP

SV = BCWP – BCWS

CI = BCWP/ACWP

SI = BCWP/BCWS

Mean = (a + 4b + c)/6, where a is the optimistic time, b is the most likely time and c is the pessimistic time

Variance = (c-a)2/36

Answers to ISQS 4350 Practice Final

| 1 | b |
| --- | --- |
| 2 | a |
| 3 | a |
| 4 | d |
| 5 | e |
| 6 | b |
| 7 | c |
| 8 | b |
| 9 | a |
| 10 | e |
| 11 | b |
| 12 | b |
| 13 | a |
| 14 | c |
| 15 | b |
| 16 | b |
| 17 | b |
| 18 | b |
| 19 | b |
| 20 | c |
| 21 | b |
| 22 | d |
| 23 | a |
| 24 | b |
| 25 | c |
| 26 | b |
| 27 | d |
| 28 | b |
| 29 | d |
| 30 | d |
| 31 | b |
| 32 | a |
| 33 | d |
| 34 | b |
| 35 | a |
| 36 | a |
| 37 | a |
| 38 | b |
| 39 | e |
| 40 | c |
| 41 | d |
| 42 | b |
| 43 | d |
| 44 | a |
| 45 | d |
| 46 | d |
| 47 | d |
| 48 | d |
| 49 | c |
| 50 | b |
| 51 | c |
| 52 | c |
| 53 | b |
| 54 | d |
| 55 | a |
| 56 | b |
| 57 | a |
| 58 | e |

- CRITICAL PATH

Activity Analysis for Practice Final

08-07-2003	Activity	On Critical	Activity	Earliest	Earliest	Latest	Latest	Slack

11:39:20	Name	Path	Time	Start	Finish	Start	Finish	(LS-ES)

1	A	Yes	3	0	3	0	3	0

2	B	no	3	3	6	9	12	6

3	C	Yes	5	3	8	3	8	0

4	D	no	4	6	10	15	19	9

5	E	no	7	8	15	12	19	4

6	F	Yes	11	8	19	8	19	0

7	G	Yes	9	19	28	19	28	0

Project	Completion	Time	=	28	weeks

Number of	Critical	Path(s)	=	1

- PERT CRASHING

{YOU VERY WELL MAY SEE A PROBLEM LIKE THIS}

- Earned Value Analysis

|  | "TODAY'S" DATE IS 12/12/2000 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| TASK | BUDGET | DURATION | %COMP | ACWP | BCWS | BCWP | CV | SV |
| A | 2000 | 5 | 60 | 1800 | 2000 | 1200 | -600 | -800 |
| B | 3000 | 6 | 70 | 2000 | 3000 | 2100 | 100 | -900 |
| C | 8000 | 10 | 50 | 4000 | 8000 | 4000 | 0 | -4000 |
| TOTALS | 13000 |  |  | 7800 | 13000 | 7300 | -500 | -5700 |
| This project is behind schedule and over budget |  |  |  |  |

HAVE A NICE DAY!!

# Text boxes

____Multiple Choice ________________________

Discussion Questions _______________________

Total         ________________________________

Adjusted Total  ____________________________

Name_________________________

A/5

D/7

B/6

C/10