## Slide 1: Chapter 11: Project Risk Management
Note: See the text itself for full citations.
Information Technology Project Management, Seventh Edition

## Slide 2
. “Only those who will risk going too far can possibly find out how far it is possible to go.” — T.S. Eliot
5. “What you have to do and the way you have to do it is incredibly simple. Whether you are willing to do it is another matter.” — Peter Drucker
Recitation

## Slide 3: Recitation
What is the greatest threat to the success of any project?
In face-to-face communications, how is most information conveyed?
  By tone of voice, by the words spoken, by the body language, by the location?
Which of the following is not a process in project communication management
  Plan communications management, manage communications, manage stakeholders, control communications

## Slide 4: Recitation
If you add three more people to a project team of five, how many more communication channels will you add?
  2, 12, 15, or 18??
A ______ report describes where a project stands at a specific point in time.
  Status, performance, forecast, earned value
What term describes information that is sent to recipients at their request via websites, bulletin boards, e-learning, knowledge repositories like blogs, etc.
  Push communications, pull communications, interactive communications, customer communications

## Slide 5: Recitation
A _________ report is a reflective statement that documents important information learned from working on the project.
Name some of the soft ‘competencies’
To avoid miscommunication get rapid feedback, as in Scrum meetings
  Short, frequent meetings are very effective in IT projects
What media choice is best for resolving a misunderstanding? (hard copy, phone call, voice mail, email, meeting, web-site)
What media choice is best for mediating a conflict? (hard copy, phone call, voice mail, email, meeting, web-site)
What media choice is best for providing a permanent record?

## Slide 6: Recitation, Cont’d
There are three processes within the communications knowledge area…name two of them

## Slide 7: Comments about Project Plans
No discussion of your break-even payback period model—assumptions and such
Often your Gantt chart did not include cost and duration columns in the associated entry table
  Some of you did not state total project duration and cost.
Some of you chose to manually schedule each task rather than specifying sequencing. This makes the Network Chart useless.
A few of you did not have 60 tasks.
By all means add milestones—at least 4
  Include a milestone for each deliverable

## Slide 8: More Comments about Project Plans
There was some over allocation of resources
  Check resource graphs
  Use RESOURCE LEVELING if necessary
Under Communications Plan I wanted you to discuss:
  Meetings—what, how often
  Documents—what, to whom, how often

## Slide 9: Learning Objectives—ch 11, Risk
Understand risk and the importance of good project risk management
Discuss the elements of planning risk management and the contents of a risk management plan
List common sources of risks on information technology (IT) projects
Describe the process of identifying risks and create a risk register
Discuss qualitative risk analysis and explain how to calculate risk factors, create probability/impact matrices, and apply the Top Ten Risk Item Tracking technique to rank risks

## Slide 10: Learning Objectives (cont’d)
Explain quantitative risk analysis and how to apply decision trees, simulation, and sensitivity analysis to quantify risks
Provide examples of using different risk response planning strategies to address both negative and positive risks
Discuss how to control risks
Describe how software can assist in project risk management

## Slide 11: The Importance of Project Risk Management
Project risk management is the art and science of identifying, analyzing, and responding to risk throughout the life of a project and in the best interests of meeting project objectives.
Risk management is often overlooked in projects, but it can help improve project success by helping select good projects, determining project scope, and developing realistic estimates.

## Slide 12: Research Shows Need to Improve Project Risk Management
Study by Ibbs and Kwak shows risk has the lowest maturity rating of all knowledge areas.
A similar survey was completed with software development companies in Mauritius, South Africa in 2003, and risk management also had the lowest maturity.
KLCI study shows the benefits of following good software risk management practices.

## Slide 13: Table 11-1. Project Management Maturity by Industry Group and Knowledge Area*
KEY: 1 = LOWEST MATURITY RATING 5 = HIGHEST MATURITY RATING
Knowledge Area | Engineering/ Construction | Telecommunications | Information Systems | Hi-Tech Manufacturing
Scope | 3.52 | 3.45 | 3.25 | 3.37
Time | 3.55 | 3.41 | 3.03 | 3.50
Cost | 3.74 | 3.22 | 3.20 | 3.97
Quality | 2.91 | 3.22 | 2.88 | 3.26
Human Resources | 3.18 | 3.20 | 2.93 | 3.18
Communications | 3.53 | 3.53 | 3.21 | 3.48
Risk | 2.93 | 2.87 | 2.75 | 2.76
Procurement | 3.33 | 3.01 | 2.91 | 3.33
*Ibbs, C. William and Young Hoon Kwak. “Assessing Project Management Maturity,”
Project Management Journal (March 2000).

## Slide 14: Figure 11-1. Benefits from Software Risk Management Practices*
*Source: Kulik and Weber, KLCI Research Group

## Slide 15: Global Issues
Many people around the world suffered from financial losses as various financial markets dropped in the fall of 2008, even after the $700 billion bailout bill was passed by the U.S. Congress.
According to a global survey of 316 financial services executives, over 70 percent of respondents believed that the losses stemming from the credit crisis were largely due to failures to address risk management issues.
They identified several challenges in implementing risk management, including data and company culture issues.

## Slide 16: Negative Risk
A dictionary definition of risk is “the possibility of loss or injury.”
Negative risk involves understanding potential problems that might occur in the project and how they might impede project success.

## Slide 17: Risk Can Be Positive
Positive risks are risks that result in good things happening; sometimes called opportunities.
A general definition of project risk is an uncertainty that can have a negative or positive effect on meeting project objectives.
The goal of project risk management is to minimize potential negative risks while maximizing potential positive risks.

## Slide 18: Best Practice
Some organizations make the mistake of only addressing tactical and negative risks when performing project risk management.
David Hillson, (www.risk-doctor.com) suggests overcoming this problem by widening the scope of risk management to encompass both strategic risks and upside opportunities, which he refers to as integrated risk management.

## Slide 19: Risk Utility
Risk utility or risk tolerance is the amount of satisfaction or pleasure received from a potential payoff.
  Utility rises at a decreasing rate for people who are risk-averse.
  Those who are risk-seeking have a higher tolerance for risk and their satisfaction increases when more payoff is at stake.
  The risk-neutral approach achieves a balance between risk and payoff.

## Slide 20: Figure 11-2. Risk Utility Function and Risk Preference

## Slide 21: Project Risk Management Processes
Plan risk management: Deciding how to approach and plan the risk management activities for the project
Identify risks: Determining which risks are likely to affect a project and documenting the characteristics of each
Perform qualitative risk analysis: Prioritizing risks based on their probability and impact of occurrence

## Slide 22: Project Risk Management Processes (cont’d)
Perform quantitative risk analysis: Numerically estimating the effects of risks on project objectives
Plan risk responses: Taking steps to enhance opportunities and reduce threats to meeting project objectives
Control risk: Monitoring identified and residual risks, identifying new risks, carrying out risk response plans, and evaluating the effectiveness of risk strategies throughout the life of the project
Information Technology Project Management, Eighth Edition

## Slide 23: Figure 11-3. Project Risk Management Summary

## Slide 24: Plan Risk Management
The main output of this process is a risk management plan—a plan that documents the procedures for managing risk throughout a project.
The project team should review project documents and understand the organization’s and the sponsor’s approaches to risk.
The level of detail will vary with the needs of the project.

## Slide 25: Table 11-2. Topics Addressed in a Risk Management Plan
Methodology
Roles and responsibilities
Budget and schedule
Risk categories
Risk probability and impact
Revised stakeholders’ tolerances
Tracking
Risk documentation

## Slide 26: Contingency and Fallback Plans, Contingency Reserves
Contingency plans are predefined actions that the project team will take if an identified risk event occurs.
Fallback plans are developed for risks that have a high impact on meeting project objectives, and are put into effect if attempts to reduce the risk are not effective.
Contingency reserves or allowances are provisions held by the project sponsor or organization to reduce the risk of cost or schedule overruns to an acceptable level; management reserves are funds held for unknown risks.

## Slide 27: Common Sources of Risk in Information Technology Projects
Several studies show that IT projects share some common sources of risk.
The Standish Group developed an IT success potential scoring sheet based on potential risks.
Other broad categories of risk help identify potential risks.

## Slide 28: Table 11-3. IT Success Potential Scoring Sheet

## Slide 29: Broad Categories of Risk
Market risk
Financial risk
Technology risk
People risk
Structure/process risk

## Slide 30: What Went Wrong?
KPMG, a large consulting firm, published a study in 1995 that found that 55 percent of runaway projects—projects that have significant cost or schedule overruns—did no risk management at all.
38 percent did some (but half did not use their risk findings after the project was underway), and
7 percent did not know whether they did risk management or not.
The timing of risk management is also an important consideration.

## Slide 31: Risk Breakdown Structure
A risk breakdown structure is a hierarchy of potential risk categories for a project.
Similar to a work breakdown structure but used to identify and categorize risks

## Slide 32: Figure 11-4. Sample Risk Breakdown Structure

## Slide 33: Table 11-4. Potential Negative Risk Conditions Associated With Each Knowledge Area

## Slide 34: Identify Risks – the second …..
Identifying risks is the process of understanding what potential events might hurt or enhance a particular project
Another consideration is the likelihood of advanced discovery
Risk identification tools and techniques include:
  Brainstorming
  The Delphi Technique
  Interviewing
  SWOT analysis

## Slide 35: Brainstorming
Brainstorming is a technique by which a group attempts to generate ideas or find a solution for a specific problem by amassing ideas spontaneously and without judgment.
An experienced facilitator should run the brainstorming session.
Be careful not to overuse or misuse brainstorming.
  Psychology literature shows that individuals produce a greater number of ideas working alone than they do through brainstorming in small, face-to-face groups.
  Group effects often inhibit idea generation.

## Slide 36: Delphi Technique
The Delphi Technique is used to derive a consensus among a panel of experts who make predictions about future developments.
Provides independent and anonymous input regarding future events.
Uses repeated rounds of questioning and written responses and avoids the biasing effects possible in oral methods, such as brainstorming.

## Slide 37: Interviewing
Interviewing is a fact-finding technique for collecting information in face-to-face, phone, e-mail, or instant-messaging discussions.
Interviewing people with similar project experience is an important tool for identifying potential risks.

## Slide 38: SWOT Analysis
SWOT analysis (strengths, weaknesses, opportunities, and threats) can also be used during risk identification.
Helps identify the broad negative and positive risks that apply to a project

## Slide 39: Risk Register
The main output of the risk identification process is a list of identified risks and other information needed to begin creating a risk register.
A risk register is:
  A document that contains the results of various risk management processes and that is often displayed in a table or spreadsheet format
  A tool for documenting potential risk events and related information
Risk events refer to specific, uncertain events that may occur to the detriment or enhancement of the project.

## Slide 40: Risk Register Contents
An identification number for each risk event
A rank for each risk event
The name of each risk event
A description of each risk event
The category under which each risk event falls
The root cause of each risk

## Slide 41: Risk Register Contents (cont’d)
Triggers for each risk; triggers are indicators or symptoms of actual risk events
Potential responses to each risk
The risk owner or person who will own or take responsibility for each risk
The probability and impact of each risk occurring.
The status of each risk

## Slide 42: Table 11-5. Sample Risk Register
• No.: R44
• Rank: 1
• Risk: New customer
• Description: We have never done a project for this organization before and don’t know too much about them. One of our company’s strengths is building good customer relationships, which often leads to further projects with that customer. We might have trouble working with this customer because they are new to us.
• Category: People risk
• Etc.

## Slide 43: Perform Qualitative Risk Analysis
The Third Process of six in the risk management knowledge area
Assess the likelihood and impact of identified risks to determine their magnitude and priority
Risk quantification tools and techniques include:
  Probability/impact matrices
  The Top Ten Risk Item Tracking
  Expert judgment

## Slide 44: Probability/Impact Matrix
A probability/impact matrix or chart lists the relative probability of a risk occurring on one side of a matrix or axis on a chart and the relative impact of the risk occurring on the other
List the risks and then label each one as high, medium, or low in terms of its probability of occurrence and its impact if it did occur
Can also calculate risk factors:
  Numbers that represent the overall risk of specific events based on their probability of occurring and the consequences to the project if they do occur

## Slide 45: Figure 11-5. Sample Probability/Impact Matrix

## Slide 46: Figure 11-6. Chart Showing High-, Medium-, and Low-Risk Technologies

## Slide 47: Top Ten Risk Item Tracking
Top Ten Risk Item Tracking is a qualitative risk analysis tool that helps to identify risks and maintain an awareness of risks throughout the life of a project.
Establish a periodic review of the top ten project risk items
List the current ranking, previous ranking, number of times the risk appears on the list over a period of time, and a summary of progress made in resolving the risk item

## Slide 48: Table 11-6. Example of Top Ten Risk Item Tracking

## Slide 49: Watch List
A watch list is a list of risks that are low priority, but are still identified as potential risks.
Qualitative analysis can also identify risks that should be evaluated on a quantitative basis.

## Slide 50: Media Snapshot
The story of the Titanic is known throughout the world, and on April 15, 2012, people acknowledged the 100th anniversary of the Titanic’s sinking.
A recent article in PMI’s Virtual Library explains how to avoid “the Titanic factor” in your projects by analyzing the interdependence of risks.
For example, the probability of one risk event occurring might change if another one materializes, and the response to one risk event might affect another.

## Slide 51: Perform Quantitative Risk Analysis
The Fourth Process of six in the Risk Management Knowledge Area
Often follows qualitative risk analysis, but both can be done together
Large, complex projects involving leading edge technologies often require extensive quantitative risk analysis
Main techniques include:
  Decision tree analysis
  Simulation models
  Sensitivity analysis

## Slide 52: Decision Trees and Expected Monetary Value (EMV)
A decision tree is a diagramming analysis technique used to help select the best course of action in situations in which future outcomes are uncertain.
Expected monetary value (EMV) is the product of a risk event probability and the risk event’s monetary value.
You can draw a decision tree to help find the EMV.

## Slide 53: Figure 11-7. Expected Monetary Value (EMV) Example

## Slide 54: Simulation Model
Simulation uses a representation or model of a system to analyze the expected behavior or performance of the system.
Monte Carlo analysis simulates a model’s outcome many times to provide a statistical distribution of the calculated results.
To use a Monte Carlo simulation, you must have three estimates (most likely, pessimistic, and optimistic) plus an estimate of the likelihood of the estimate being between the most likely and optimistic values.

## Slide 55: Steps of a Monte Carlo Analysis
Assess the range for the variables being considered
Determine the probability distribution of each variable
For each variable, select a random value based on the probability distribution
Run a deterministic analysis or one pass through the model
Repeat steps 3 and 4 many times to obtain the probability distribution of the model’s results

## Slide 56: Figure 11-8. Sample Monte Carlo Simulation Results for Project Schedule

## Slide 57: What Went Right?
A large aerospace company used Monte Carlo simulation to help quantify risks on several advanced-design engineering projects, such as the National Aerospace Plane (NASP).
The results of the simulation were used to determine how the company would invest its internal research and development funds.
See text for examples of how General Motors, Eli Lily, and Proctor & Gamble use simulation software

## Slide 58: Sensitivity Analysis
Sensitivity analysis is a technique used to show the effects of changing one or more variables on an outcome.
For example, many people use it to determine what the monthly payments for a loan will be given different interest rates or periods of the loan, or for determining break-even points based on different assumptions.
Spreadsheet software, such as Excel, is a common tool for performing sensitivity analysis

## Slide 59: Figure 11-9. Sample Sensitivity Analysis for Determining Break-Even Point

## Slide 60: Planning Risk Responses
After identifying and quantifying risks, you must decide how to respond to them.
Four main response strategies for negative risks:
  Risk avoidance
                Just use the old system
  Risk acceptance
                Have a backup or contingency plan
  Risk transference
                Purchase insurance or a warranty
  Risk mitigation
                Reduce the impact or the probability of occurrence

## Slide 61: Table 11-7. General Risk Mitigation Strategies for Technical, Cost, and Schedule Risks

## Slide 62: Response Strategies for Positive Risks
Risk exploitation
    Focus on the upside potential
Risk sharing
    Find a partner to share with
Risk enhancement
    Increase the upside potential
Risk acceptance
    Run with the risk

## Slide 63: Residual and Secondary Risks
It’s also important to identify residual and secondary risks.
Residual risks are risks that remain after all of the response strategies have been implemented.
Secondary risks are a direct result of implementing a risk response.

## Slide 64: Control Risks – the Sixth…
Involves executing the risk management process to respond to risk events and ensuring that risk awareness is an ongoing activity performed by the entire project team throughout the entire project
Workarounds are unplanned responses to risk events that must be done when there are no contingency plans.
Main outputs of risk control are:
  Work performance information
  change requests
  updates to the project management plan, other project documents, and organizational process assets

## Slide 65: Using Software to Assist in Project Risk Management
Risk registers can be created in a simple Word or Excel file or as part of a database
More sophisticated risk management software, such as Monte Carlo simulation tools, help in analyzing project risks
You can purchase add-ons for Excel and Project 2013 to perform simulations.

## Slide 66: Results of Good Project Risk Management
Unlike crisis management, good project risk management often goes unnoticed.
Well-run projects appear to be almost effortless, but a lot of work goes into running a project well.
Project managers should strive to make their jobs look easy to reflect the results of well-run projects.

## Slide 67: Chapter Summary
Project risk management is the art and science of identifying, analyzing, and responding to risk throughout the life of a project and in the best interests of meeting project objectives.
Main processes include:
  Plan risk management
  Identify risks
  Perform qualitative risk analysis
  Perform quantitative risk analysis
  Plan risk responses
  Control risks