## Slide 1: Best Practices: or BETTER Practices??
James R. Burns

## Slide 2: Introduction
Best Practices as found in the literature on Project Management
Best Practices are practices that are considered ‘optimal’ at this juncture in time
But Best Practices are continually being IMPROVED…..so in a sense we never ever arrive…
Thus, the BEST PRACTICES continually get ….BETTER
Better and Better

## Slide 3: Consider the Proverbial Process
Best Practice
Inputs
Outputs

## Slide 4: About PMBOK
BMPOK has little to say about the practices that make up the 44 processes that are identified—instead it….
Leaves that to its users, knowing that such practices will be forever changing
It does identify the inputs and outputs to each process—because these are pretty-well fixed

## Slide 5: Does your organization have a ‘Best Practice’ Champion?
If not, your organization is not very ‘mature’
Volunteer to become one—
  BE PROACTIVE -- Covey
  TAKE INITIATIVE – Kelley
Such a champion might be variously called ‘process champion’, ‘maturity champion’, etc.

## Slide 6: As a Best Practice Champion, you will
Document the existing practice
Get everyone in your organization to use that practice
Form a Change Control Committee
Use PDCA
Continually improve the practices

## Slide 7: Deming Wheel: PDCA Cycle

## Slide 8: Summary of Today’s Session
To learn some concepts that we’ve never seen before
To review some concepts that we’ve seen many times before

## Slide 9: Ten oft-recited Best Practices
Determine requirements (specifications)
Plan the work by utilizing a project requirements document
Create a planning horizon
Define project management practices up front

## Slide 10: Ten old Best Practices , Cont’d
Do your Risk Management Due Diligence
Guard against Scope Creep
Continue to assess risks throughout the project
Resolve issues quickly
Execute according to plan—monitor and control Schedule and Budget
Motivate your team!!!

## Slide 11: Agenda of New Best Practices
Change Board
Daily Build and Smoke test
Designing for Change
Evolutionary prototyping
Goal setting
Inspections
Joint Applications Development (JAD)
Lifecycle Model Selection
Measurement
Miniature Milestones
Outsourcing
Principled Negotiation

## Slide 12: More New Best Practices
Productivity Environments
Rapid Development Languages
Requirements Scrubbing
Reuse, Reuse, Reuse
Productivity Environments
Staged Delivery
Theory-W Management
Throwaway Prototyping
Time-box Development
Tools Group
Top-10 Risks List
User-Interface Prototyping
Voluntary Overtime

## Slide 13: Overview
How do we overcome some of the biggest problems associated with IT Projects
  Customers don’t know what they want
  Absence of progress visibility
  No one knows exactly what is involved
  How long it will take or how much it will cost is not known

## Slide 14: Connections
All of these best practices fit together to create a kind of synergism

## Slide 15: Change Control Board
We’ve said about everything there is to say about this best practice
An odd-numbered committee, so as to avoid ties when voting
Every-faction represented—including the customer

## Slide 16: Daily Build and Smoke Test {DBST}
Microsoft’s not-so secret weapon
  If MS could evangelize one software engineering idea, this would be it
  Most germane to large software development projects, like MS Windows….

## Slide 17: DBST Efficacy
  potential reduction from nominal schedule
  improved progress visibility (progress monitoring)
  decreased schedule risk and quality risk
  very good chance for first time success/excellent chance of long term success
  Supports easier defect diagnosis
  Improves overall product quality

## Slide 18: DBST Risks
  DBST reduces integration risk, quality risks, while increasing progress visibility
  Pressure to release interim versions of a program too frequently

## Slide 19: Daily Build and Smoke Test
You build the product every day and test it minimally every day (off line)
If the build (compile, link) to create an executable doesn’t work, it is considered broken and becomes the highest priority of the team to get fixed
  a clean build is one in which all source files compile to object modules
  all files link successfully
  smoke test is passed

## Slide 20: Daily Build and Smoke Test
Is treated as the heartbeat of the project
Uses an automated build tool such as make in VB
On large projects someone on the team has responsibility for conducting the daily build and smoke test
DBST’s are performed in the evening and if successful released the next morning for use by the team

## Slide 21: Daily Build and Smoke Test
Virtually any kind of project can use daily builds--large, small, shrink-wrap software and business systems
On Windows NT 3.0, there were four full-time people in the build group
NT 3.0 has 5.6 million lines of code spread across 40,000 modules
  The DBST took 19 hours even though it was spread across several machines
  Still, the team managed to build and test every day
  Much of the success was attributed to the DBST

## Slide 22: Smoke Test
Smoke test grows with the sophistication of the program
Smoke test involves an exercise of the entire system from end-to-end
Not an exhaustive test
Detects (surfaces) major problems
If a build passes a smoke test, it is stable enough to be tested and is a good build

## Slide 23: Designing for Change
modest potential reduction in nominal schedule
no improvement in progress visibility
decreased schedule risk
good chance of first/time success/excellent chance of long-term success

## Slide 24: Designing for Change
Because it is very difficult to get requirements right the first time
Customers don’t know what they want
Requirements modeling has improved requirements determination, but still there are many problems

## Slide 25: Designing for Change
Enables changes late in the project to be effected easily, rapidly
Change can happen because of market conditions, the customer’s understanding of the problem changes, or the technology changes etc.

## Slide 26: Designing for Change
Identify areas likely to change
use information hiding
  this contains/confines the change inside/within a single module
  Set boundaries on inheritance
  Create a plug-and-play software landscape
Develop a change plan
Define families of programs

## Slide 27: Designing for Change/risk management
such changes make maintenance much easier
means good program structure and high quality code
Supports evolutionary/incremental/versioned delivery
  Giving your customers a piece of functionality at a time

## Slide 28: Evolutionary Delivery
Establish a stable, static core architecture for the product, the application
Deliver the customer’s first understanding of the problem early
Also could be called early delivery
This gets some functionality into the hands of the customer or end user at an early date

## Slide 29: Evolutionary Delivery--Advantages
Reduces the risk of delivering a product the customer doesn’t want, avoiding time-consuming rework
For custom software, it makes progress visible by delivering software early and often
For shrink-wrap commercial software, it supports more frequent product releases
It reduces estimation error by allowing for recalibration and re-estimation after each evolutionary delivery

## Slide 30: Evolutionary Delivery—Advantages
It reduces the risk of integration problems by integrating early and often—whenever a delivery occurs
It improves morale because the project is seen as a success from the first time the product is delivered
Improves your ability to make mid-course corrections

## Slide 31: Goal setting
Makes use of the fact that human motivation is the single, strongest contributor to productivity
In Goal Setting, a project manager or customer simply tells developers what is expected of them

## Slide 32: Goal setting – efficacy
Potential for reduction from nominal schedule—very good
Chance for first-time success—good
Chance of long-term success—very good
Considered GOOD OVERALL in terms of creating a shorter schedule

## Slide 33: Inspections
These are formal technical reviews in which participants in the review are well-trained in review practices and assigned specific roles to play
The roles played during the review meeting help to stimulate discovery of additional errors
Have been found to be much more effective in finding errors than execution testing
  Both in percentage of total defects found and in time spent per defect

## Slide 34: Inspections—in relation to rapid development
Detection of errors early
Avoids costly downstream work
Can be used on both development and maintenance

## Slide 35: Joint Applications Development (JAD)

## Slide 36: Lifecycle Model Selection
Choose the wrong lifecycle and what happens??
Choose the right lifecycle and what happens??

## Slide 37: Wrong lifecycle
Missing tasks
Inappropriate tasks
Tasks in the wrong order

## Slide 38: Right lifecycle
All tasks are there
All tasks are in the right order
Energy and effort is used effectively

## Slide 39: Measurement
A Goldratt soapbox
Time-after-time Goldratt finds companies that are failing because they are measuring and rewarding the wrong things
Is the antidote to the common problems of poor estimates, poor scheduling, and poor progress visibility
Has the potential to reduce the duration of the project schedule, improve progress visibility, and reduce schedule risk

## Slide 40: Measurement {M}
Firms should institute a measurement group
Measurement should provide status (progress) visibility
M should focus people’s activities
  People get focused on visible measurements that are rewarded
  What gets measured and rewarded, gets optimized
M should improve morale
M can help set realistic expectations
M lays the groundwork for process improvement

## Slide 41: Software Measures
Size in lines of code
  What do you think would happen if you rewarded people for the number of lines of code they put out per week?
Size in function points
Defects per thousand lines of code
Hours spend analyzing, designing, coding, testing
Developer satisfaction
Developer stress

## Slide 42: Measurement
Doesn’t produce results within the span of one project, but over several projects, processes and practices are improved
There is a tendency to measure everything just in case you need it
A better practice is to allow measurements to be driven by goals, questions, and metrics

## Slide 43: Goals:
A good one is to reduce the number of defects that make their way into the software initially
  Which then take so much time to find and remove later

## Slide 44: Miniature Milestones
Is a fine-grained approach to project tracking and control that provides exceptional visibility into a project’s status
Eliminates the risk of uncontrolled, undetected schedule slippage
Works well when used with the daily build and smoke test

## Slide 45: Miniature Milestones--Advantages
Can be used throughout the development lifecycle, not just the construction phase
Works well with just about any kind of software development
Provides developers with a steady sense of accomplishment

## Slide 46: Miniature Milestones
Are obviously milestones that are between major milestones
Provides visibility and confidence that major milestones will be reached
EVERYONE BECOMES AWARE THAT A PROJECT IS GOING TO SLIP MUCH SOONER

## Slide 47: Miniature Milestones
Improves visibility
Provides fine-grain control
Improves motivation
Reduces schedule risk
“Never let a developer go DARK!!!”

## Slide 48: Outsourcing
There are folks outside who can do it better, faster and less money than the folks inside
Outside sources may have solved the problem many times before and therefore be much further down on the learning curve
Outside sources may be able to extensively reuse

## Slide 49: Principled Negotiation
Seeks WIN/WIN agreements
Removes problems from people and seeks solutions outside of those problems

## Slide 50: Productivity Environments (PE)
Provide developers the freedom from noise and interruptions they need in order to work effectively
  Because software development is a highly intellectual activity that requires long periods of uninterrupted concentration

## Slide 51: PE -- Quiet, uninterrupted work
Surprisingly, more than 70% of all software organizations have crowded office conditions and the average time between interruptions was 11 minutes

## Slide 52: PE – Flow time
Developers require 15 minutes or more to enter a state of flow which can then last for many hours, until fatigue or interruption terminates it
If developers are interrupted every 11 minutes, they will likely never enter a flow state, referred to as “IN THE ZONE”

## Slide 53: Productivity environments – Specifications
At least 80 sq. ft. of floor space
At least 15 sq. ft. of desk space
At least 15 linear feet of bookshelf space
An external window
At least 12 sq. ft. of whiteboard space
At least 12 sq. ft. of bulletin board space

## Slide 54: PE--Convenient access….
To other team members
To a high-speed printer
To a photocopy machine
To conference rooms
To common office supplies

## Slide 55: PE—Some means of…
Stopping phone interruptions

## Slide 56: Rapid Development Languages
Can improve productivity greatly

## Slide 57: Requirements Scrubbing
This is using the Pareto 80/20 rule to….

## Slide 58: Requirements scrubbing
After you create a req. specification, you go over it with a fine tooth comb:
  Eliminate all reqs. that are not absolutely necessary
  Simplify all requirements that are more complicated than necessary
  Substitute cheaper options for all requirements that have cheaper options

## Slide 59: Reuse
90% reduction in development time
Greatly increased quality
Requires the right kind of culture
What would that culture be??

## Slide 60: Signing Up

## Slide 61: Spiral Lifecycle Model
Developed by Barry Bhoem, this is a risk-driven methodology that requires several iterations through a cycle to complete a project, each iteration requiring a testing or inspection stage.
Brings testing into the development lifecycle much sooner, reducing risk

## Slide 62: Staged Delivery
This is similar to evolutionary delivery

## Slide 63: Theory-W Management
Make every one a winner
Plan the flight and fly the plan
Software PM’s will be successful only if they make winners of all the other participants in the software process: superiors, subordinates, customers, users, maintainers, etc.

## Slide 64: Throwaway Prototyping
Develop the prototype quickly
Test it
Throw it away
Take what you learned and use it to develop the final version of the software

## Slide 65: Timebox Development
Developed by Dupont
The basis for many RAD methodologies
  SCRUM
  RUP

## Slide 66: Tools Group

## Slide 67: Top-10 Risks List

## Slide 68: User-Interface Prototyping

## Slide 69: Voluntary Overtime

## Slide 70: Feature Set Control (FSC)
Discussed on next slides

## Slide 71: FSC -- Creeping requirements
How to handle the problem of creeping requirements
  Requirements that are added late in a product’s development
  A common source of cost and schedule overruns
  A major factor in project cancellations

## Slide 72: FSC -- Late breaking changes leads to late software
PERIOD—end of discussion!!~!||!!

## Slide 73: Three kinds of Feature Set Control
Early-project control involves defining a feature set that is consistent with your project’s schedule of budget objectives
Mid-project control involves controlling creeping requirements
Late-project control of trimming features to meet a schedule or cost goal

## Slide 74: FSC--One reason for project success
The project manager was keenly aware of the need to control late-breaking software changes.
He hung this sign over his desk

## Slide 75: NO!
(What Part of this don’t you understand)

## Slide 76: EARLY PROJECT: The first commandment of Rapid Development is to narrow your scope
Minimal specification
Requirements scrubbing
Versioned development

## Slide 77: Minimal specification
Wasted specification effort
  You can waste an enormous amount of time specifying details that users don’t care about
Obsolescence
  Changes mid-way through a project can quickly render a requirements document obsolete

## Slide 78: More on minimal specification
The goal is not to build exactly what you said you would at the beginning
It is to build the best possible software within the available time
Too often developers spend time on stuff the user’s don’t want, don’t need, don’t care about

## Slide 79: More on minimal specification
Lack of efficacy
  Specifying a system in enormous detail is insufficient to guarantee success
Overly constrained design
  Forces design and implementation approaches that waste time, waste money

## Slide 80: Minimal specifications, when used properly should produce
Improved morale and motivation
  There is a great contribution to developer morale
Opportunistic efficiency
  With a minimal spec, developers are more free to design and implement the software in the most expeditious way possible

## Slide 81: Risks of minimal requirements
Omission of key requirements
  You risk leaving out things that the customer does care about
Unclear or impossible goals
  Crystal-clear goals are essential to the success of minimal reqs.
  Goals tell developers how to resolve ambiguities
    Maximum “WOW”
    Or Minimum development TIME???

## Slide 82: Gold-plating
  Developers start specifying most of the product themselves
  Every postmortem at Microsoft brings up the complaint that developers couldn’t resist adding new features, resulting in schedule problems

## Slide 83: Versioned development
Scrubbing may postpone some requirements for a later version
Inevitably, when you get to version 2, you will scrap some of the features you had originally planned for version 2 and add others

## Slide 84: MID-PROJECT: Feature-Creep Control
A typical project experiences about a 25-percent change in reqs. during development (Boehm 1981, Jones 1994)

## Slide 85: Sources of Change
End-users want changes because they want additional functionality
Marketers want changes because they see the market as feature driven
Developers want changes because they have a great emotional and intellectual investment in all of the system’s details.

## Slide 86: Killer App syndrome
A few weeks before an app is to go to production, its competition comes out with a list of features that the developers never thought about

## Slide 87: Unclear or impossible goals
We want to develop a world-class product in the shortest possible time at the lowest possible cost

## Slide 88: Unclear specifications: consider a graphics program that uses Polymarkers
Size of polymarkers (15 ways to do this)
  Don’t provide any control at all
  Set up source code to be modified in one place for the polymarkers
  Allow for the modification of a text file that the system reads upon startup
  Allow for interactive end-user modification
Implementation time can vary tremendously based on how developers interpret seemingly trivial details

## Slide 89: REPEAT: Implementation time and cost can vary tremendously based on interpretation of specs
  In this case the devil really is in the details
  Studies have found 10 to 1 differences in the sizes of programs written to the same specification
  What is required are guidelines related to goals that take developers toward #1 or toward #4 when there are ambiguities
If you tend toward #1 rather than toward #4, your program could be easily created an order of magnitude faster and cheaper

## Slide 90: Effects of Change
People are far too casual about the effects that late changes in a project have.
Developers underestimate the ripple effects that changes have on the project’s design, code, testing, documentation, customer support, training, configuration management, personnel assignments, and schedule budgets, and product qualtiy

## Slide 91: Late-breaking changes
Cost from 50 to 200 times more if you make them during construction or maintenance as opposed to the requirements phase.
FEATURE CREEP IS THE MOST COMMON SOURCE OF COST AND SCHEDULE OVERRUNS

## Slide 92: The WISDOM of avoiding changes altogether
Nice work if you can get it
However, there are situations in which it is unwise to disallow changes altogether
  When your customers don’t know what they want
    What kind of contractual arrangement is best here???
  For most projects, it is not possible to absolutely know the requirements?
    For these, try incremental development

## Slide 93: When you want to be responsive to your customer
If you follow a frozen requirements plan, you might deliver the product on time, but you might seem unresponsive, and that can be just as bad as late delivery

## Slide 94: When the market is changing rapidly
Rather than automatically trying to eliminate requirements changes, the software developer’s job today is to strike a balance between chaos and rigidity
Again, use short release cycles, like Microsoft does
  This incremental development approach is a type of evolutionary development and is very helpful

## Slide 95: When you want to give latitude to the developers
Since the PC revolution, developers have been empowered to make a lot of the detail decisions themselves as they move through the development

## Slide 96: Stable requirements?
Don’t think your requirements are stable when they aren’t

## Slide 97: Methods of Change Control: GOALS
Allow changes that help to produce the best possible product in the time available
Allow all parties that would be affected by a proposed change to assess the schedule
Notify parties on the periphery of the project of each proposed change
Provide an audit trail of decisions related to the product content

## Slide 98: Use a change board—BEST PRACTICE
Consists of representatives from each party that has a stake in the product’s development

## Slide 99: Summary
State what has been learned
Define ways to apply training

## Slide 100: Where to get more information
Other training sessions
Books, articles, electronic sources
Consulting services, other sources

## Slide 101: References
References
1. McConnell, Steve, RAPID DEVELOPMENT, Redmond, Washington: Microsoft Press, 1996.
2. DeMarco, Tom, CONTROLLING SOFTWARE PROJECTS, New York: Yourdon Press, 1982.
3. Martin, James, RAPID APPLICATION DEVELOPMENT, New York: Mcmillan Publishing Company, 1991.
4. Basili, Victor R., and David M. Weiss, 1984. “A Methodology for Collecting Valid Software Engineering Data.” IEEE Transactions on Software Engineering SE-1, no. 4 (December): 390-396.

## Slide 102: More References
5. Brodman, Judith G., and Donna L. Johnson, 1995. “Return on Investment (ROI) from Software Process Improvement as Measured by US Industry.” Software Process, August: 36-47.
6. McConnell, Steve, CODE COMPLETE, Redmond, Washington: Microsoft Press, 1993.

## Slide 103: Feedback
Request feedback of training session